## Summary
Revit vs CAD Technical QC
Project | Test Tower
Revit model | test.rvt
CAD folder | /tmp/cadqc_test_87e50d611c58425f99107f1094424321
Run (local time) | 2026-09-26 05:23
Duration (s) | 0.6
Severity | Open issues
Critical | 1
Major | 5
Minor | 3
Info | 0
Resolved since last run | 0
Category | Open issues
Wall | 3
Column | 1
Door | 1
Window | 1
Dimension | 1
Revit Model | 1
Room | 1

## Issues
Id | Status | Severity | Floor | Level | Category | Issue | Title | CAD value | Revit value | Delta (mm) | Revit X | Revit Y | Revit ids | CAD layer | Description
L02-WAL-002 | New | Critical | 2nd Floor | Second Floor | Wall | Missing in Revit | Wall 115 mm thick, 4713 mm long not modelled in Revit | 115 mm × 4713 mm | — | 4712.5 | 103421.3 | -41096.8 |  | A-WALL | The CAD wall on layer 'A-WALL' (115 mm thick, 4713 mm long) has no Revit wall within 400 mm.
L02-COL-001 | New | Major | 2nd Floor | Second Floor | Column | Position offset | Column shifted 60 mm |  |  | 59.6 | 105547.2 | -44487.9 | 3002 | S-COLS | Column centre differs by 59.6 mm between CAD and Revit.
L02-DR-001 | New | Major | 2nd Floor | Second Floor | Door | Width mismatch | Door width: CAD 900 mm vs Revit 1000 mm | 900 mm | 1000 mm — Single 1000 | 100 | 103605.1 | -46244.3 | 2001 | A-DOOR | Door D1: CAD width 900 mm (from swing arc radius), Revit 'Single 1000' width 1000 mm.
L02-WAL-001 | New | Major | 2nd Floor | Second Floor | Wall | Thickness mismatch | Wall thickness: CAD 230 mm vs Revit 200 mm | 230 mm drawn, note "230 THK. BRICK WALL" | 200 mm — Brick 230 | -30 | 100240.2 | -45242.3 | 1005 | A-WALL | CAD wall (230 mm drawn, note "230 THK. BRICK WALL") is modelled with Revit type 'Brick 230' (200 mm) over 4713 mm.
L02-WAL-003 | New | Major | 2nd Floor | Second Floor | Wall | Extra in Revit (not in CAD) | Revit wall 'Brick 115' (2885 mm) not in CAD | — | Brick 115, 2885 mm | 2885 | 105716.4 | -44901.2 | 1006 |  | Revit wall 1006 of type 'Brick 115' has no matching wall in the CAD plan.
L02-WIN-001 | New | Major | 2nd Floor | Second Floor | Window | Missing in Revit | Window W1 (1200 mm) missing in Revit | W1 1200 mm | — | 1200 | 106524.7 | -46100.5 |  | A-GLAZ | CAD window (block 'WIN_1200', layer 'A-GLAZ', width from block extents) has no Revit window within 600 mm.
L02-DIM-001 | New | Minor | 2nd Floor | Second Floor | Dimension | Dimension mismatch | Dimension 230 mm in CAD, 200 mm in Revit | 230 mm | 200 mm | -30 | 98866.4 | -46035.3 | 1005 | A-ANNO-DIMS | CAD dimension between wall face and wall face reads 230 mm; the same references in Revit are 200 mm apart.
L02-MDL-001 | New | Minor | 2nd Floor | Second Floor | Revit Model | Type name does not match width | Type 'Brick 230' is actually 200 mm wide |  | Brick 230: 200 mm | -30 | 100214.9 | -45257.1 | 1005 |  | The wall type name suggests 230 mm but the type width is 200 mm.
L02-RM-001 | New | Minor | 2nd Floor | Second Floor | Room | Name mismatch | Room name: CAD 'KITCHEN' vs Revit 'Dining' | KITCHEN | 202 Dining |  | 99539.5 | -46801.4 | 5002 | A-AREA-IDEN | Revit room 202 is named 'Dining'.

## Floors
Floor | Revit level | CAD file | Plan title | Alignment | Match % | RMS mm | Issues | CAD Walls | Revit Walls | CAD Doors | Revit Doors | CAD Windows | Revit Windows | CAD Columns | Revit Columns | CAD Rooms | Revit Rooms | CAD Grids | Revit Grids
2nd Floor | Second Floor | 2ND FLOOR PLAN.dxf | SECOND FLOOR PLAN | Grid intersections | 91.1 | 4.3 | 9 | 9 | 7 | 1 | 1 | 1 | 0 | 2 | 2 | 2 | 2 | 4 | 4